## Team1_Estimated_Effort
[9 empty] | Seth | Blake | Brandon | Ryan | Total
Iterations/Sections |  | Task | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 7
|  | Design architecture | Project Manager | Seth, Blake, Brandon | 12 |  | 7 |  | 3 | 3 | 1 | 0 | 7
| Requirements |  |  |  |  | 9 |  | 4.5 |  |  |  |  | 0
|  | Gather | Researchers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Analyze | Researchers | Seth, Blake, Brandon | 4 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Specify | Researchers | Seth, Blake, Brandon | 3 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
| Documentation |  |  |  |  | 28 |  | 27.5 |  |  |  |  | 0
|  | Requirements Document | Researchers | Brandon | 3 |  | 3.5 |  | 0 | 0 | 3.5 | 0 | 3.5
|  | Project Plan Document | Researchers | Brandon | 3 |  | 4 |  | 0 | 0 | 4 | 0 | 4
|  | Architecture Document | Researchers | Brandon | 5 |  | 2.5 |  | 0 | 0 | 2.5 | 0 | 2.5
|  | Test Plan Document | Researchers | Blake, Brandon | 3 |  | 3 |  | 0 | 2 | 1 | 0 | 3
|  | Test Cases Document | Researchers | Blake, Brandon | 3 |  | 3 |  | 0 | 2 | 1 | 0 | 3
|  | Test Report Document | Researchers | Blake, Brandon | 4 |  | 3 |  | 0 | 2 | 1 | 0 | 3
|  | Team Effort Estimation Document | Researchers | Brandon, Seth | 3 |  | 3.5 |  | 0.5 | 0 | 3 | 0 | 3.5
|  | User Guide Document | Researchers | Brandon | 2 |  | 3 |  | 0 | 0 | 3 | 0 | 3
|  | Project PowerPoint | Researchers | Brandon, Seth, Blake | 2 |  | 2 |  | 0.5 | 0.5 | 1 | 0 | 2
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: Deliv 1 | Development |  |  |  |  | 16 |  | 15.5 |  |  |  |  | 0
|  | Determine technology needs | Researchers | Blake, Seth, Brandon | 2 |  | 2.5 |  | 1 | 1 | 0.5 | 0 | 2.5
|  | Research and learn new language and environment | Programmers | Seth, Brandon | 10 |  | 10 |  | 5 | 5 | 0 | 0 | 10
|  | Create Github Repository | Project Manager | Seth | 1 |  | 0.5 |  | 0.5 | 0 | 0 | 0 | 0.5
|  | Set Up File System structure | Programmers | Blake, Seth | 2 |  | 2 |  | 1 | 1 | 0 | 0 | 2
|  | Create Installation File for Flask setup | Programmers | Blake | 1 |  | 0.5 |  | 0.5 | 0 | 0 | 0 | 0.5
| Analysis |  |  |  |  | 3 |  | 5 |  |  |  |  | 0
|  | Ensure everyone can get set up properly | Programmers | Seth, Blake, Brandon, Ryan | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Evaluate needs for next iteration | Project Manager | Seth | 1 |  | 1 |  | 1 | 0 | 0 | 0 | 1
Iteration 2: Deliv 2/3 | Design |  |  |  |  | 2 |  | 2 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Seth | 2 |  | 2 |  | 2 | 0 | 0 | 0 | 2
| Development |  |  |  |  | 25 |  | 23.5 |  |  |  |  | 0
|  | Create SQLite Database | Programmers | Blake | 4 |  | 4 |  | 0 | 4 | 0 | 0 | 4
|  | Setup SQLite Database to work within Flask | Programmers | Blake | 3 |  | 2 |  | 0 | 2 | 0 | 0 | 2
|  | Create Prototype Web Page | Programmers | Blake, Seth | 5 |  | 6 |  | 3 | 3 | 0 | 0 | 6
|  | Create Routes for future web pages | Programmers | Blake, Seth | 3 |  | 3 |  | 1.5 | 1.5 | 0 | 0 | 3
|  | Create Navigation Bar | Programmers | Blake, Seth | 4 |  | 3 |  | 1 | 2 | 0 | 0 | 3
|  | Create prototype flowchart for website | Programmers | Brandon | 2 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Create basic CSS stylesheet, pair it with HTML files | Programmers | Brandon | 2 |  | 1.5 |  | 0 | 0 | 1.5 | 0 | 1.5
|  | Unit Testing | Programmers | Blake | 2 |  | 2 |  | 0 | 2 | 0 | 0 | 2
| Analysis |  |  |  |  | 6 |  | 6 |  |  |  |  | 0
|  | System Testing | Programmers | Blake, Seth, Brandon | 3 |  | 3 |  | 1 | 1 | 1 | 0 | 3
|  | Bug fix as required | Programmers | Blake, Seth, Brandon | 2 |  | 2 |  | 1 | 1 | 0 | 0 | 2
|  | Evaluate needs for next iteration | Project Manager | Seth | 1 |  | 1 |  | 1 | 0 | 0 | 0 | 1
Iteration 3: Deliv 4 | Design |  |  |  |  | 7 |  | 5.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Seth | 2 |  | 1 |  | 1 | 0 | 0 | 0 | 1
|  | Risk analysis | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Start making stylistic choices for the website | Programmer | Brandon | 3 |  | 3 |  | 0 | 0 | 3 | 0 | 3
| Development |  |  |  |  | 29 |  | 27.5 |  |  |  |  | 0
|  | Review requirements | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Create user registration form/page | Programmers | Blake, Seth, Brandon | 4 |  | 4.5 |  | 2 | 2 | 0.5 | 0 | 4.5
|  | Create user login form/page | Programmers | Blake, Seth | 3 |  | 3 |  | 1 | 2 | 0 | 0 | 3
|  | Create user account page | Programmers | Seth, Blake | 8 |  | 7 |  | 6 | 1 | 0 | 0 | 7
|  | Create add courses option for user registration | Programmers | Blake, Seth, Brandon | 4 |  | 4 |  | 2 | 1 | 1 | 0 | 4
|  | Create Section for User Account Info Changing | Programmers | Seth | 2 |  | 1.5 |  | 1.5 | 0 | 0 | 0 | 1.5
|  | Create/Manage CSS Classes | Programmers | Brandon, Seth | 3 |  | 3 |  | 1.5 | 0 | 1.5 | 0 | 3
|  | Create color pallette | Programmers | Brandon | 1 |  | 1 |  | 0 | 0 | 1 | 0 | 1
|  | Unit Testing | Programmers | Blake | 2 |  | 2 |  | 0 | 2 | 0 | 0 | 2
| Analysis |  |  |  |  | 7 |  | 7 |  |  |  |  | 0
|  | System Testing | Programmers | Blake, Seth, Brandon | 3 |  | 3 |  | 1 | 1 | 1 | 0 | 3
|  | Bug Fix as required | Programmers | Blake, Seth, Brandon | 2 |  | 2 |  | 0.5 | 1 | 0.5 | 0 | 2
|  | Evaluate needs for next iteration | Project Manager | Seth | 2 |  | 2 |  | 2 | 0 | 0 | 0 | 2
Iteration 4: Deliv 5 | Design |  |  |  |  | 7 |  | 5.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Seth | 2 |  | 1 |  | 1 | 0 | 0 | 0 | 1
|  | Risk analysis | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Discuss/determine job listings layout | Programmers | Seth, Blake, Brandon | 3 |  | 3 |  | 1 | 1 | 1 | 0 | 3
| Development |  |  |  |  | 21 |  | 21.5 |  |  |  |  | 0
|  | Review requirements | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Create/Manage Job Listing Style | Programmers | Seth, Brandon | 2 |  | 2 |  | 1.5 | 0 | 0.5 | 0 | 2
|  | Create Search Bar | Programmers | Seth, Blake | 4 |  | 4 |  | 1 | 3 | 0 | 0 | 4
|  | Create Filters | Programmers | Blake, Seth | 4 |  | 4 |  | 1 | 3 | 0 | 0 | 4
|  | Create Job Listing Template | Programmers | Blake, Seth | 2 |  | 3 |  | 1 | 2 | 0 | 0 | 3
|  | Create Jobs Page | Programmers | Blake, Seth, Brandon | 3 |  | 3 |  | 1 | 1 | 1 | 0 | 3
|  | Style Search Bar | Programmers | Seth, Brandon | 2 |  | 2 |  | 1 | 0 | 1 | 0 | 2
|  | Unit Testing | Programmers | Blake | 2 |  | 2 |  | 0 | 2 | 0 | 0 | 2
| Analysis |  |  |  |  | 6 |  | 5.5 |  |  |  |  | 0
|  | System Testing | Programmers | Blake, Seth, Brandon | 3 |  | 3 |  | 1 | 1 | 1 | 0 | 3
|  | Bug fix as required | Programmers | Blake, Seth, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Evaluate needs for next iteration | Project Manager | Seth | 1 |  | 1 |  | 1 | 0 | 0 | 0 | 1
Iteration 5: Deliv 6 | Design |  |  |  |  | 4 |  | 2.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Seth | 2 |  | 1 |  | 1 | 0 | 0 | 0 | 1
|  | Risk analysis | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
| Development |  |  |  |  | 8 |  | 7.5 |  |  |  |  | 0
|  | Review requirements | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Create Application Form/Page | Programmers | Blake, Seth | 2 |  | 2 |  | 1 | 1 | 0 | 0 | 2
|  | Create My Applications Page | Programmers | Blake, Seth | 2 |  | 2 |  | 1 | 1 | 0 | 0 | 2
|  | Unit Testing | Programmers | Blake | 2 |  | 2 |  | 0 | 2 | 0 | 0 | 2
| Analysis |  |  |  |  | 8 |  | 7 |  |  |  |  | 0
|  | System Testing | Programmers | Blake, Seth, Brandon | 3 |  | 3 |  | 1 | 1 | 1 | 0 | 3
|  | Bug Fix as required | Programmers | Blake, Seth, Brandon | 3 |  | 3 |  | 1 | 1 | 1 | 0 | 3
|  | Evaluate needs for next iteration | Project Manager | Seth | 2 |  | 1 |  | 1 | 0 | 0 | 0 | 1
Iteration 6: Deliv 7 | Design |  |  |  |  | 10 |  | 8.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Seth | 2 |  | 1 |  | 1 | 0 | 0 | 0 | 1
|  | Discuss/Determine Administration Page | Programmers | Seth, Blake, Brandon | 6 |  | 6 |  | 2 | 2 | 2 | 0 | 6
|  | Risk analysis | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
| Development |  |  |  |  | 17 |  | 16.5 |  |  |  |  | 0
|  | Review requirements | Programmers | Seth, Blake, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Create Administration Page Layout | Programmers | Seth, Blake | 3 |  | 3 |  | 1.5 | 1.5 | 0 | 0 | 3
|  | Implement Create Job Listing Functionality | Programmers | Blake | 2 |  | 2 |  | 0 | 2 | 0 | 0 | 2
|  | Implement Application Management Functions | Programmers | Seth, Blake, Brandon | 5 |  | 5 |  | 3 | 1 | 1 | 0 | 5
|  | Implement Existing User Views | Programmers | Blake, Seth, Brandon | 1 |  | 1 |  | 0 | 1 | 0 | 0 | 1
|  | Implement Edit Job Listing Management | Programmers | Blake, Seth | 2 |  | 2 |  | 1 | 1 | 0 | 0 | 2
|  | Unit Testing | Programmers | Blake | 2 |  | 2 |  | 0 | 2 | 0 | 0 | 2
| Analysis |  |  |  |  | 8 |  | 7.5 |  |  |  |  | 0
|  | System Testing | Programmers | Blake, Seth, Brandon | 2 |  | 1.5 |  | 0.5 | 0.5 | 0.5 | 0 | 1.5
|  | Bug fix as required | Programmers | Blake, Seth, Brandon | 6 |  | 6 |  | 2 | 2 | 2 | 0 | 6
Totals | [5 empty] | 233 |  | 206 | 76.5 | 82 | 53.5 | 1 | 213